## Sheet1
Appendix 1
Mapesbury Dell Doorstep Green
Site Creation Capital Costs
Note: Timing is dependent upon availability of grant
| Year and Season | Creation Plan Paragraph | Description | Area/Number | Unit Meaure | Unit Cost | Estimated Actual Cost | Gross inc 10% Contigency | Gifft in Kind Value (if not actual Cost) | Volunteer work time @£50 oer day | Total Volunteer Time
Phase 1 Works
| Spring | 10.2 | Preliminaries and site set out | 1 |  | 500 | 465 | 511.5
| Spring | 10.2 | Soft preparations and skimming of 50mm | 1 |  | 2500 | 2325 | 2557.5
| Spring | 10.2 | Breaking up and Removing Existing Tarmac | 1 |  | 1600 | 1488 | 1636.8
| Spring | 10.2 | Excavations for all bases and sub-bases | 1 |  | 5400 | 5022 | 5524.2
| Spring | 10.2 | Skip space and barrowing out | 1 |  | 4900 | 4557 | 5012.7
| Spring | 10.8 | Hard Paths | 1 | 200m2 | 15100 | 14043 | 15447.3
| Spring | 10.8 | Secondary woodland paths | 1 | 75m2 | 4985 | 4636.05 | 5099.655
| Spring | 10.9 | Ponds with balance tanks | 1 |  | 3650 | 3394.5 | 3733.95
| Spring | 10.8 | Hard landscape/Cobble sets | 1 | 87m2 | 11000 | 10230 | 11253
| Spring | 10.10 | Childrens Planters | 1 |  | 2215 | 2059.95 | 2265.945
| Spring | 10.10 | Sandpit | 1 |  | 550 | 511.5 | 562.65
| Spring | 10.10 | Play ship/hut/barrels etc. | 1 |  | 6000 | 5580 | 6138
| Spring | 10.10 | Play Logs | 1 |  | 250 | 232.5 | 255.75
| Spring | 10.10 | Childrens Bark Area | 1 | 10m2 | 275 | 255.75 | 281.325
| Spring | 10.8 | Lawn | 1 |  | 500 | 465 | 511.5
| Sprng | 10.8 | Bedworks , groundworks, soiling up & composting | 1 |  | 6000 | 5580 | 6138
| Spring | 10.8 | Machinery | 1 |  | 2500 | 2325 | 2557.5
1 | Spring | 10.10 | Sanded beach & pebble play area | 1 |  | 2500 | 2325 | 2557.5
| Spring | 10.8 | Fixing benches, bins etc. | 1 |  | 600 | 558 | 613.8
| Spring | 10.11 | Picnic Table and benches | 3 |  | 1450 | 4045.5 | 4450.05
| Spring | 10.11 | Bins | 4 |  | 865 | 3217.8 | 3539.58
| Spring | 10.11 | Benches | 11 |  | 550 | 5626.5 | 6189.15
| Spring | 10.11 | Seats | 6 |  | 350 | 1953 | 2148.3
| Spring | 10.13 | Signage | 1 |  | 1250 | 1162.5 | 1278.75
| Spring | 10.12 | Trees Shrubs & Planting | 1 |  | 12500 | 11625 | 12787.5 |  | 40 | 1250
| Sub-Total | [5 empty] | 93683.55 | 103051.905 |  |  | 1250
Phase 2 Works
| Spring | 10.3 | Brick walls and copings at entrance | 1 |  | 1750 | 1750 | 1925
| Spring | 10.4 | Brick Walls on either side of entrance passageway | 120 | m2 | 125 | 15000 | 16500
| Spring | 10.3 | Gates | 1 |  | 3550 | 3550 | 3905
| Spring | 10.4 | Paving Entranceway and passage | 1 | m2 | 9000 | 9000 | 9900
| Spring | 10.6 | Sculpture/Entrance Feature | 1 |  | 6500 | 6500 | 7150
| Spring | 10.7 | Elegant Storage/Utility Hut | 1 |  | 8500 | 8500 | 9350
| Spring | 10.5 | Electricity Supply | 1 |  | 3000 | 3000 | 3300
| Spring | 10.5 | Water Supply | 40 | m | 130 | 5200 | 5720
| Spring | 10.5 | Irrigation | 1 |  | 3500 | 3500 | 3850
| Sub-Total | [5 empty] | 56000 | 61600 |  |  | 0
| Total | [5 empty] | 149683.55 | 164651.905 |  |  | 1250