## Sheet2
Children Bill
Draft Macro Project Plan v1 4th Oct - Details managed by lead officer |  |  | Week ending | 2004-07-16 | 2004-07-23 | Week ending | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
PROJECT OVERVIEW AND CO-ORDINATION | Lead Officer | Hours/Days |  |  |  | Week ending | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Roles and Responsibilities | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Gareth Daniel
2004-10-18
Draft Project plan for integration of children's services to be agreed.
Senior Member Officer Group established to implement bill | [6 empty] | In place
Potential risks to project plan implementation identified
Identify and allocate project plan tasks to lead officers | [6 empty] | 2004-10-04 | 2004-10-18
Process established for deciding structural 'Model' agreed by SMOG
TOR and Membership for Children's Partnership Board (CPB) agreed
Structural 'Model' for integration presented to Council Executive by SMOG
Consult/inform PCT, Stakeholders, Staff, Schools,
Identifying Servcies to be integrated
Governance issues (see legal)
Visit Knowsley investigate virtual model.
[12 empty] | CMT |  | Leaders | Executive
[14 empty] | Briefing | 2004-10-13
Evaluation Process to be developed
(Developing Systems and Processes) | Lead Officer | [17 empty] | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
| (GD) | [13 empty] | 2004-12-13
Establish scope of services to be integrated (SMOG)
Strategic plan for key services being integrated completed.
Strategic plan for other council services affected by integration.
Strategic Plan disseminated to Council Executive,Key Partners/Stakeholders
Joint Commissioning and Strategy unit as per JG diagram
Political management of the process, cabinet portfolios
CORPORATE AND STRUCTURAL | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Choice of Model | Gareth Daniel | [17 empty] | 2004-02-25: CEO Paper
Analysis of effect of model chosen on other departments and services | [17 empty] | FebO5
Dof CS define role, likely to be board level.
2 groups to look at model, SMOG and project group led by CEO.
Explore external partnerships (see above, see legal, see HR)
Service intergration, Rik, Janet reporting to SMOG and CPB
Co-location, explore civic centre possible co-location site with PCT
EXTERNAL PARTNERSHIPS | bar: 2004-01-07 to 2004-01-28
Issues around Model chosen
Key partners and stakeholders identified
Consultation, on roles, governance arrangements, identify lead responsibilities
Clear terms of reference and written constitution established
Legal criteria for use of Section 31 agreements
Agreement reached with partners timeline for review for all arrangements regularly
System for monitoring use of budgets and activity established.
Safeguarding Children agenda to be developed within Children's Partneship Board.
FINANCE | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Duncan McLeod
Develop Financial Plan | Duncan McLeod
Map process for resources allocated to delivering servcies for children and young people, report headlines to CPG/SMOG
Identify resources available for potential pooled funds
Process for dissaggregating of relevant exisiting budgets identified. (e.g. by service type, mental health service or between children and adults)
Finance aware of impact of joint commissioning strategy decisions.
Baseline budgets agreed and recorded into partnership arrnagements for fixed period with reviews
IT and accomodation
Decision on how host authority will monitor budget.
Lobby Government for grant
Negotiate with partner agencies
Need information, map how resources currently distributed
Single principles paper onSection 31, budget and governance
Risk assessment completed
Consult with schools (new rules in 2006)
Identify/ understand Capital investment
Outline budget process
Identify PCT opportunities for more K funding
Report to SMOG and Executive (by January 2005)
Investigation of efficiencies in joint commisioning/ procurement
HUMAN RESOURCES | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Valerie Jones
Develop Human Resources Plan | Valerie Jones
In Post
Identify other posts which may be required
Assess Impact of integration on external, non children's services
Develop workforce plans and new training and devleopment
Renumeration packages for new roles
Enhanced roles for support staff
ADCP in post 18/10/04
Advertise for Director of Childrens Services to recruit by May | [18 empty] | 2004-01-07: Advertise
Impact of this post on CMT and HR | [18 empty] | 2004-01-07: for DCS
Lead Member in place by May 05, impact on other lead member roles
Decision on top structures by December for Executive
Rik and Janet reporting on servcies for integration
Sure Start to come into Council
PCT staff to stay with PCT agreement reached
DevelopTraining packages for all staff affected
PROFESSIONAL PRACTICE ISSUES | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Jenny Goodall
Common Assessment Framework (CAF) to be developed | DirSS Dir Ed
CAF - develop plan once gov't guidance received. | Krutika Pau
ISA - training required for all staff | Manveen Patwalia
Extended schools project group to be set up by? | Susan McKenzie
Resourcing -Identification of realistic bid to Awaydays completed by?
Safeguarding children to be identified as separate issue in project plan | Jenny Goodall
Co-location of teams professional practice issues to be identified. | Jenny Goodall
Information presented to SMOG by ? | Jenny Goodall
Information Sharing and Assessment (ISA) protocol completed
Develop protocol which is Freedom of Information Act compatible
Research results from Pathfinders and Non Pathfinders on ISA
Map cross agency information on children currently held In Brent
Consider data protection issues, Caldicatt Guardian requirements
Ensure all staff are trained and sign up to new protocol
Scope financial implications of ISA
Extended Schools
Consultation with schools for Extended school status
Mapping servcies to be provided/services needed
Mapping of current projects/servcies in schools
Goals for servcie provision agreed by all stakeholders
Services identified and planned
Evaluation process developed with regualr review points
COMMUNICATION AND CONSULTATION | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Communication | Toni McConvile
Communication Strategy/ Plan completed
Process for regular briefings to Executive, and Council
Corporate Identity and Branding, develop identity of new service.
Service development plans
Start communication on timeframe and framework of change
Partners timeframe - identfied involvement completed by?
Team set up to work on this by ? (T.McC, OT, ?KM others identifed by?)
Consultation | Owen Thomson
Consultation strategy/Plan completed with attention to the following issues.
Regular process for consultation with all parties put in place
Consult with service users and Council staff on changes.
Consult with External Stakeholders partners
Staff consultation -
CPB work on outcomes completed by?
Consultation with Children and Young People, OT paper to SMOG
Which issues staff are to be consulted on decided by?
Identify relevant existing structures for consultation, especially with stakeholders
LEGAL ISSUES | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
Terri Osborne
(Council and External Partnerships)
Governance
Establish new authority, responsibility and accountability for services
Develop role of Children's Services Director and Lead Council Member with clear accountabilities
Decision reached on whether connexions Partnerships will use Children's Trust as its local management committee
Written agreement or constitution for Children's Trust completed
Set up Children's Safeguarding Partnership Board
Identify legal powers to enter into partnerships, and our Section 31 powers
Establish if YOT and Connexions are covered by Section 31
Set standard partnerships agreements for integrated services, and framework for partnerships
Establish if joint Committee is required for Section 31 agreements
Identify if Overview and Scrutiny function should be merged
Changes presented to Scrutiny at May 05 meeting
Outline timetable for CMT, Executive, F.P. Select Committee include in Forward Plan
Change of job descriptions and terms and conditions of staff, identify impacts.
Staff Union and other consultation
Information sharing
Other legal issues pending, Exended schools,Statutory role of DSS,DCS,DED,CEX
Director of Children's Services role/responsbilities defined.
Cross Party presentation
Identify restrictions on non council functions
Corporate Governance
All bodies accountabilities built on the corporate governance arrangements of partner agencies
All bodies (and individuals) within trust or other partnership arrangement to complete an account of Objectives and
Priorities, Perfromance, Proper use of money, Quality of Services
Work Practice Governance
Clinical Governance, (NHS) and Care Practice (SS) joint frameworks put in place
Practice Standards and clear policies and procedures for joint working developed and regular monitoring system put in place
Complaints procedure established for new joint working.
Contracts and Service Agreements
Transfer of Contracts for joint services like IT support, equipment, etc transferred to relevant agency
Clarify legal oversight of GIS mapping of projects/needs analysis
SERVICE SPECIFIC ISSUES | Lead Officer | [5 empty] | 2004-10-15 | 2004-10-22 | 2004-10-29 | 2004-11-05 | 2004-11-12 | 2004-11-19 | 2004-11-26 | 2004-12-03 | 2004-12-10 | 2004-12-17 | 2004-12-24 | 2004-12-31 | 2004-01-07 | 2004-01-14 | 2004-01-21 | 2004-01-28 | 2004-02-04 | 2004-02-11 | 2004-02-18 | 2004-02-25 | 2004-03-04 | 2004-03-11 | 2004-03-18 | 2004-03-25 | 2004-04-01 | 2004-04-08 | 2004-04-15 | 2004-04-22 | 2004-04-29 | 2004-05-06 | 2004-05-13 | 2004-05-20 | 2004-05-27 | 2004-06-03 | 2004-06-10 | 2004-06-17 | 2004-06-24 | 2004-07-01 | 2004-07-08 | 2004-07-15
AD CSS AD Ed
Preparatory work
Preventative Strategy developed and circulated/consulted on
CPG outcomes developed into Pis
Joint Commissioning Strategy developed and circulated/consutled on
Demographic needs analysis completed
Children's consultation findings incorporated into final strategy for integration of servcies
Strategic Safeguarding Partnership Board set up and Membership expanded as necessary
Consultation on Children's Centres and Extended Schools completed
Co-located teams pilots (CAMHS, CWD) set up and running