## Revenue Implications (hidden)
The tables below demonstrate the revenue implications of the unsupported borrowing included in the forecast capital programme.
General Fund Capital Programme | 2005/06 | 2006/07 | 2007/08 | 2008/09
| £'000 | £'000 | £'000 | £'000
2004/05
Agreed Unsupported Borrowing £14.259m | 1511.454 | 1497.195 | 1497.195 | 1497.195
Of which Self Funded £0.417m | -44.202 | -43.785 | -43.785 | -43.785
2005/06
Agreed Unsupported Borrowing £12.927m | 439.518 | 1370.262 | 1357.335 | 1357.335
2006/07
Agreed Unsupported Borrowing £13.134m | 0 | 446.556 | 1392.204 | 1379.07
2007/08
Agreed Unsupported Borrowing £12.300m | 0 | 0 | 418.2 | 1303.8
2008/09
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
Cumulative Total | 1906.77 | 3270.228 | 4621.149 | 5493.615
Housing Revenue Account Capital Programme | 2005/06 | 2006/07 | 2007/08 | 2008/09
| £'000 | £'000 | £'000 | £'000
2004/05
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
2005/06
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
2006/07
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
2007/08
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
2008/09
Agreed Unsupported Borrowing £0m | 0 | 0 | 0 | 0
Cumulative Total | 0 | 0 | 0 | 0
The charges to revenue accounts represent the estimated interest payable on the borrowing required to
balance the capital programme, ie those capital expenditure items not supported by central government
funding, grants from external bodies and income derived from capital receipts.
The financing charges that have been applied to unsupported capital borrowing are as follows:-
Year 1 3.4%
Year 2 10.6%
Year 3 10.5%
These rates have amended the guidance laid down in the 2004/2005 Budget Preparation Paper. The
principle element of the charge is based on the Minimum Revenue Provision requirement laid down in
accounting practices, which is currently set at 4%, with the balance relating to the interest charge which is
based on the Consolidated Loan Pool Rate, this takes into account the interest rates on all principle sums
owing by the Council. The rate of 3.4% in Year 1 is based on a half year charge for interest and no
repayment of principle.

## Comp Forecast to November Posit (hidden)
FORECAST CAPITAL PROGRAMME 2005/06 & FUTURE YEARS
General Fund
|  | 2004/05 | 2004/05 | 2004/05 | 2005/06 | 2005/06 | 2005/06
|  | Nov Exec | Revised | Budget | First Reading | Revised | Budget
| Programme Details | Budget | Budget | Variance | Report | Budget | Variance
|  | £000 | £000 | £000 | £000 | £000 | £000
RESOURCES:
Supported Borrowing - General Fund:
| Central Government - SCE (R) | -6946 | -7385 | -439 | -7518 | -5825 | 1693
| Central Government - SCE (C) | -5428 | -5751 | -323 | -1690 | -2401 | -711
| Environment Grant Income | -5129 | -5129 | 0 | -5000 | -5000 | 0
| Disabled Facilities Grant | 0 | -1247 | -1247 | 0 | -1270 | -1270
| Capital Receipts in Year | -5658 | -5055 | 603 | -500 | -4400 | -3900
| Capital Funding Account | 0 | 0 | 0 | -300 | -300 | 0
| S106 Funding | -3483 | -3619 | -136 |  | -1401 | -1401
| Local Authority Social Housing Grant Transitional Grant | 0 | -200 | -200 |  | -200 | -200
| 2004/05 Capital Programme (Surplus)/Deficit Carry Fwd | -11770 | -19677 | -7907 | -330 | -6112 | -5782
| Revenue Contributions to Capital Outlay | -20 | -20 | 0 |  | 0 | 0
| Agreed Unsupported Borrowing - General Fund | -13874 | -13842 | 32 | -12927 | -12927 | 0
| Unsupported Borrowing (Self Funded Schemes) | -385 | -417 | -32 | 0 | -150 | -150
| Unsupported Borrowing (Self Funded - Schools Partnering Scheme) | -2000 | 0 | 2000 | 0 | -2000 | -2000
| Unsupported Borrowing required to meet Budget Deficit | 0 | 0 | 0 | -7291 | 0 | 7291
| Total Resources | -54693 | -62342 | -7649 | -35556 | -41986 | -6430
EXPENDITURE:
Education, Arts and Libraries:
| Investment Plan | 11252 | 15936 | 4684 | 7489 | 12186 | 4697
| Schools Partnering Scheme (Self Funded) | 2000 | 0 | -2000 | 2000 | 2000 | 0
| Total Educ, Arts and Libs | 13252 | 15936 | 2684 | 9489 | 14186 | 4697
Environment :
| Grant Funded Schemes | 5129 | 5129 | 0 | 5000 | 5000 | 0
| Investment Plan | 10712 | 10007 | -705 | 5275 | 6495 | 1220
| Approved Capitalisation of Revenue Expenditure | 0 | 0 | 0 | 0 | 200 | 200
| Total Environment | 15841 | 15136 | -705 | 10275 | 11695 | 1420
Social Services:
| Investment Plan | 1945 | 1157 | -788 | 2308 | 1156 | -1152
| Total Social Services | 1945 | 1157 | -788 | 2308 | 1156 | -1152
Housing: General Fund
| PSRSG and DFG council | 5000 | 5000 | 0 | 5300 | 5350 | 50
| New Units | 3969 | 3969 | 0 | 3969 | 3969 | 0
| Chalkhill Redevelopment | 258 | 221 | -37 | 0 | 0 | 0
| Investment Plan | 2397 | 2416 | 19 | 800 | 800 | 0
| Total Housing | 11624 | 11606 | -18 | 10069 | 10119 | 50
Corporate Services:
| Investment Plan | 4627 | 4071 | -556 | 690 | 1110 | 420
| Self Funded Schemes | 0 | 0 | 0 | 0 | 150 | 150
| Total Corporate Services | 4627 | 4071 | -556 | 690 | 1260 | 570
| Total Service Expenditure | 47289 | 47906 | 617 | 32831 | 38416 | 5585
Central Items:
| Retention's | 300 | 300 | 0 | 300 | 300 | 0
| Provision for Liabilities | 850 | 850 | 0 | 0 | 0 | 0
| Deferred Purchase | 659 | 659 | 0 | 659 | 659 | 0
| Grange Road Acquisition | 140 | 140 | 0 | 0 | 0 | 0
| Surestart | 42 | 42 | 0 | 0 | 0 | 0
| Elm Road Car Park Lease | 250 | 250 | 0 | 0 | 0 | 0
| Property Leases (Slippage) | 700 | 700 | 0 | 0 | 0 | 0
| Estate Access Corridor | 4133 | 5383 | 1250 | 766 | 766 | 0
| Inspections of Non-Housing Property | 0 | 0 | 0 | 0 | 80 | 80
| South Kilburn - Councils Contribution | 0 | 0 | 0 | 1000 | 1000 | 0
| Total Central Items | 7074 | 8324 | 1250 | 2725 | 2805 | 80
| Overall Total Expenditure | 54363 | 56230 | 1867 | 35556 | 41221 | 5665
| (Surplus)/Deficit | -330 | -6112 | -5782 | 0 | -765 | -765
FORECAST CAPITAL PROGRAMME 2005/06 & FUTURE YEARS
Housing Revenue Account
|  | 2004/05 | 2004/05 | 2004/05 | 2005/06 | 2005/06 | 2005/06
| Programme Details | Nov Exec | Revised | Budget | First Reading | Revised | Budget
|  | Budget | Budget | Variance | Report | Budget | Variance
|  | £000 | £000 | £000 |  | £000
RESOURCES
Supported Borrowing - Housing Revenue Account:
| Central Government - SCE (R) | -5264 | -5264 | 0 | -5264 | -6224 | -960
| ALMO Round 2 - Year 3 | -22500 | -22500 | 0 | -11500 | -11250 | 250
| ALMO Round 2 - Top Up | 0 | 0 | 0 | 0 | -8997 | -8997
| ALMO Round 4 | 0 | 0 | 0 | 0 | -14000 | -14000
| Unsupported Borrowing - Housing Revenue Account: | 0 | 0 | 0 | 0 | 0 | 0
| Total Resources | -27764 | -27764 | 0 | -16764 | -40471 | -23707
EXPENDITURE:
Housing Revenue Account
| ALMO | 27764 | 27764 | 0 | 16764 | 40471 | 23707
| South Kilburn Regeneration | 0 | 0 | 0 |  | 0 | 0
| Total Expenditure | 27764 | 27764 | 0 | 16764 | 40471 | 23707
| (Surplus)/Deficit | 0 | 0 | 0 | 0 | 0 | 0

## 0607 Forecast Programme
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
|  | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
| Programme Details | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
RESOURCES: GENERAL FUND
Capital Grants and other contributions
| Government Grant - SCE (C) | -2520 | -3076 | -3076 | -3076 | 0 | -2555 | -2555 | 0 | -2600 | -2640
| Devolved Formula Capital | -3290 | -5266 | -5266 | -5335 | -69 | -3458 | -3458 | 0 | -3460 | -3460
| Other External Grant | -10361 | -16560 | -21075 | -20935 | 140 | -12760 | -13635 | -875 | -7781 | -6501
| Capital Receipts in Year - Right to Buy Properties | -1750 | -1750 | -1750 | -1750 | 0 | -1750 | -1750 | 0 | -1750 | -1750
| Corporate Property Disposals | -3000 | -4071 | -4071 | -4071 | 0 | -2000 | -2000 | 0 | -2000 | -2000
| Other Receipts | -495 | -695 | -695 | -695 | 0 | -200 | -200 | 0 | -200 | -200
| Capital Funding Account | 0 | -2105 | -2105 | -2105 | 0 | 0 | 0 | 0 | 0 | 0
| S106 Funding | -1688 | -5199 | -5199 | -2788 | 2411 | -1888 | -2434 | -546 | -1635 | 0
Borrowing
| Supported Borrowing - SCE (R) | -7866 | -7866 | -7866 | -7866 | 0 | -8125 | -8125 | 0 | -8410 | -8700
| Unsupported Borrowing | -12317 | -12257 | -12257 | -9579 | 2678 | -12312 | -14915 | -2603 | -7257 | -8369
| Unsupported Borrowing (Self Funded Schemes) | 0 | -150 | -150 | -150 | 0 | 0 | 0 | 0 | 0 | 0
| Total Resources | -43287 | -58995 | -63510 | -58350 | 5160 | -45048 | -49072 | -4024 | -35093 | -33620
EXPENDITURE: GENERAL FUND
Children & Families
| School Schemes | 14927 | 15048 | 18468 | 14767 | -3701 | 17018 | 21117 | 4099 | 11003 | 9630
| Non - School Schemes | 50 | 548 | 548 | 548 | 0 | 0 | 0 | 0 | 0 | 0
| Ringfenced Grant Notifications | 282 | 282 | 282 | 282 | 0 | 331 | 331 | 0 | 0 | 0
| Childrens Centre Sure Start Grant | 2161 | 2161 | 2161 | 2161 | 0 | 2020 | 2020 | 0 | 0 | 0
| LEA Controlled Voluntary Aided Programme | 0 | 0 | 1095 | 1095 | 0 | 1191 | 1191 | 0 | 0 | 0
| Devolved Formula Capital | 3290 | 5266 | 5266 | 5335 | 69 | 3458 | 3458 | 0 | 3460 | 3460
| Total Children & Families | 20710 | 23305 | 27820 | 24188 | -3632 | 24018 | 28117 | 4099 | 14463 | 13090
Environment & Culture
| TfL Grant Funded Schemes | 5501 | 5963 | 5963 | 5963 | 0 | 5501 | 5501 | 0 | 5501 | 5501
| Waste Performance and Efficiency Grant | 302 | 302 | 302 | 302 | 0 | 317 | 317 | 0 | 0 | 0
| Estate Access Corridor | 0 | 2105 | 2105 | 2105 | 0 | 0 | 0 | 0 | 0 | 0
| Stadium Access Corridor | 0 | 5108 | 5108 | 5108 | 0 | 0 | 0 | 0 | 0 | 0
| Leisure & Sports Schemes | 300 | 405 | 405 | 405 | 0 | 0 | 0 | 0 | 0 | 0
| Environmental Initiative Schemes | 0 | 478 | 478 | 478 | 0 | 0 | 0 | 0 | 0 | 0
| Highways Schemes | 3320 | 3374 | 3374 | 3374 | 0 | 2888 | 2888 | 0 | 2900 | 3000
| Parks & Cemeteries Schemes | 700 | 744 | 1082 | 956 | -126 | 450 | 450 | 0 | 700 | 700
| Library Schemes | 0 | 576 | 576 | 987 | 411 | 0 | 0 | 0 | 0 | 0
| Total Environment & Culture | 10123 | 19055 | 19393 | 19678 | 285 | 9156 | 9156 | 0 | 9101 | 9201
Housing & Community Care: Adults
| Adult Personnal Social Services Schemes | 425 | 544 | 544 | 329 | -215 | 0 | 0 | 0 | 0 | 0
| Ringfenced Grant Notifications | 175 | 175 | 175 | 180 | 5 | 0 | 175 | 175 | 0 | 0
| Total Housing & Community Care: Adults | 600 | 719 | 719 | 509 | -210 | 0 | 175 | 175 | 0 | 0
Housing and Community Care: Housing
| PSRSG and DFG council | 5600 | 6340 | 6340 | 6340 | 0 | 5300 | 5300 | 0 | 5300 | 5300
| New Units | 2969 | 2969 | 2969 | 2969 | 0 | 2969 | 2969 | 0 | 2969 | 2969
| Customer Services Schemes | 0 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0
| Total Housing & Community Care: Housing | 8569 | 9363 | 9363 | 9363 | 0 | 8269 | 8269 | 0 | 8269 | 8269
Corporate
| ICT Schemes | 225 | 723 | 723 | 723 | 0 | 425 | 425 | 0 | 0 | 0
| Property Schemes | 2060 | 3740 | 3652 | 3739 | 87 | 1930 | 1930 | 0 | 2260 | 2060
| South Kilburn - Councils Contribution | 1000 | 2000 | 2000 | 0 | -2000 | 1000 | 1000 | 0 | 1000 | 1000
| Self Funded Schemes | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
| Total Corporate | 3285 | 6613 | 6525 | 4612 | -1913 | 3355 | 3355 | 0 | 3260 | 3060
| Total Service Expenditure | 43287 | 59055 | 63820 | 58350 | -5470 | 44798 | 49072 | 4274 | 35093 | 33620
| Surplus carried forward | 0 | 60 | 310 | 0 | -310 | -250 | 0 | 250 | 0 | 0
| Deficit to be funded | 0 | 60 | 310 | 0 | -310 | -250 | 0 | 250 | 0 | 0
CAPITAL PROGRAMME 2006/07 TO 2009/10
Housing Revenue Account
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Capital | Capital
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast | Programme | Programme
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
RESOURCES: HOUSING REVENUE ACCOUNT
Supported Borrowing
| RHB Allocation - SCE (R) | -6500 | -6500 | -6500 | -6500 | 0 | -6500 | -6500 | 0 | -6500 | -6500
| ALMO Round 4 | 0 | -3455 | -3455 | -3455 | 0 | 0 | 0 | 0 | 0 | 0
| Unsupported Borrowing | 0 | 0 | 0 | 0 | 0 | -11900 | -11900 | 0 | 0 | 0
| Total Resources | -6500 | -9955 | -9955 | -9955 | 0 | -18400 | -18400 | 0 | -6500 | -6500
EXPENDITURE: HOUSING REVENUE ACCOUNT
Housing Revenue Account
| ALMO | 6500 | 9955 | 9955 | 9955 | 0 | 6500 | 6500 | 0 | 6500 | 6500
| South Kilburn Regeneration | 0 | 0 | 0 | 0 | 0 | 11900 | 11900 | 0 | 0 | 0
| Total Expenditure | 6500 | 9955 | 9955 | 9955 | 0 | 18400 | 18400 | 0 | 6500 | 6500
| (Surplus)/Deficit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CAPITAL PROGRAMME 2006/07 TO 2009/10
Summary of Position
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Capital | Capital
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast | Programme | Programme
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
RESOURCES
| General Fund | -43287 | -58995 | -63510 | -58350 | 5160 | -45048 | -49072 | -4024 | -35093 | -33620
| Housing Revenue Account | -6500 | -9955 | -9955 | -9955 | 0 | -18400 | -18400 | 0 | -6500 | -6500
| Total Resources | -49787 | -68950 | -73465 | -68305 | 5160 | -63448 | -67472 | -4024 | -41593 | -40120
EXPENDITURE:
| General Fund | 43287 | 59055 | 63820 | 58350 | -5470 | 44798 | 49072 | 4274 | 35093 | 33620
| Housing Revenue Account | 6500 | 9955 | 9955 | 9955 | 0 | 18400 | 18400 | 0 | 6500 | 6500
| Total Expenditure | 49787 | 69010 | 73775 | 68305 | -5470 | 63198 | 67472 | 4274 | 41593 | 40120
| Surplus carried forward | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deficit (to be funded) | 0 | 60 | 310 | 0 | -310 | -250 | 0 | 250 | 0 | 0

## Resources
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Resources
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Supported Borrowing - General Fund:
| Central Government - SCE (R) | -7866 | -7866 | -7866 | -7866 | 0 | -8125 | -8125 | 0 | -8410 | -8700
| Central Government - SCE (C) | -2520 | -3076 | -3076 | -3076 | 0 | -2555 | -2555 | 0 | -2600 | -2640
| Devolved Formula Capital | -3290 | -5266 | -5266 | -5335 | -69 | -3458 | -3458 | 0 | -3460 | -3460
| LEA Controlled Voluntary Aided Programme | 0 | 0 | -1095 | -1095 | 0 | -1191 | -1191 | 0 | 0 | 0
| Childrens Centres Sure Start Grant | -2161 | -2161 | -2161 | -2161 | 0 | -2020 | -2020 | 0
| Environment Grant Income (Borough Spending Plan) | -5501 | -5963 | -5963 | -5963 | 0 | -5501 | -5501 | 0 | -5501 | -5501
| Waste Performance and Efficiency Grant | -302 | -302 | -302 | -302 | 0 | -317 | -317 | 0 | 0 | 0
| Chalkhill Account Reserve (Funding Housing) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Disabled Facilities Grant | -1140 | -1140 | -1140 | -1140 | 0 | -1000 | -1000 | 0 | -1000 | -1000
| Stadium Access Corridor Funding (SRB/LDA/S106) | 0 | -5108 | -5108 | -5108 | 0 | 0 | 0 | 0 | 0 | 0
| Sport England Grant (Education) | 0 | -167 | -167 | -167 | 0 | 0 | 0 | 0 | 0 | 0
| Additional Grant Notifications (Ringfenced): |  |  |  |  | 0 |  |  | 0
| Children & Families - Youth Capital Grant | -126 | -126 | -126 | -126 | 0 | -126 | -126 | 0 | 0 | 0
| - Integrated Childrens System IT Capital | -156 | -156 | -156 | -156 | 0 | -205 | -205 | 0 | 0 | 0
Housing and Community Care: Adults -
| Improving Information Management Grant | -175 | -175 | -175 | -180 | -5 | 0 | -175 | -175 | 0 | 0
| Targeted Capital Funding (Education) | -800 | -800 | -4220 | -3918 | 302 | -2400 | -3100 | -700 | -1280 | 0
| NHFM (Libraries) Grant Funding 2006/07 | 0 | -462 | -462 | -619 | -157 | 0 | 0 | 0 | 0 | 0
| Capital Receipts in Year - Right to Buy Properties | -1750 | -1750 | -1750 | -1750 | 0 | -1750 | -1750 | 0 | -1750 | -1750
| Former LRB/Ex-GLC Properties | -200 | -400 | -400 | -400 | 0 | -200 | -200 | 0 | -200 | -200
| Corporate Property Disposals | -3000 | -4071 | -4071 | -4071 | 0 | -2000 | -2000 | 0 | -2000 | -2000
| Grange Museum Related Receipts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project C Related Receipts | -295 | -295 | -295 | -295 | 0 | 0 | 0 | 0 | 0 | 0
| Capital Funding Account | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Children and Families S106 Funding | -1688 | -5199 | -5199 | -1306 | 3893 | -1888 | -2434 | -546 | -1635 | 0
| EAC S106 funding | 0 | 0 | 0 | -1482 | -1482 | 0 | 0 | 0 | 0 | 0
| Local Authority Social Housing Grant Transitional Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2004/05 Capital Programme (Surplus)/Deficit Carry Fwd | 0 | -2105 | -2105 | -2105 | 0 | 0 | 0 | 0 | 0 | 0
| Revenue Contributions to Capital Outlay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Agreed Unsupported Borrowing - General Fund | -12317 | -12257 | -12257 | -9579 | 2678 | -12312 | -14915 | -2603 | -7257 | -8369
| Unsupported Borrowing (Self Funded Schemes) | 0 | -150 | -150 | -150 | 0 | 0 | 0 | 0 | 0 | 0
| Total Resources | -43287 | -58995 | -63510 | -58350 | 5160 | -45048 | -49072 | -4024 | -35093 | -33620
FORECAST CAPITAL PROGRAMME 2005/06 TO 2008/09
Housing Revenue Account - Resources
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
RESOURCES
Supported Borrowing - Housing Revenue Account:
| Central Government - SCE (R) | -6500 | -6500 | -6500 | -6500 | 0 | -6500 | -6500 | 0 | -6500 | -6500
| ALMO Round 4 | 0 | -3455 | -3455 | -3455 | 0 | 0 | 0 | 0 | 0 | 0
| Unsupported Borrowing - Housing Revenue Account: | 0 | 0 | 0 | 0 | 0 | -11900 | -11900 | 0 | 0 | 0
| Total Resources | -6500 | -9955 | -9955 | -9955 | 0 | -18400 | -18400 | 0 | -6500 | -6500

## Children & Families
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Children and Families Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
|  | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
| Programme Details | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
| Devolved Capital | 3290 | 5266 | 5266 | 5335 | 69 | 3458 | 3458 | 0 | 3460 | 3460
Additional Grant Notifications (Ringfenced):
| Children & Families - Youth Capital Grant | 126 | 126 | 126 | 126 | 0 | 126 | 126 | 0 | 0 | 0
| - Integrated Childrens System IT Capital | 156 | 156 | 156 | 156 | 0 | 205 | 205 | 0 | 0 | 0
| Additional Grant Notifications (Ringfenced): | 282 | 282 | 282 | 282 | 0 | 331 | 331 | 0 | 0 | 0
| Childrens Centre Sure Start Grant | 2161 | 2161 | 2161 | 2161 | 0 | 2020 | 2020 | 0 | 0 | 0
| LEA Controlled Voluntary Aided Programme | 0 | 0 | 1095 | 1095 | 0 | 1191 | 1191 | 0 | 0 | 0
2005/06 and Future Years Capital Programme
Individual School Schemes
| St Mary Magdalen's Junior School Rebuild (TCF Funded) | 800 | 800 | 800 | 100 | -700 | 2400 | 3100 | 700 | 1280 | 0
| The Avenue Primary School (TCF Funded) | 0 | 0 | 3420 | 3420 | 0 | 0 | 0 | 0 | 0 | 0
| Jesus and Mary Language College and Cardinal Hinsley RC High School (TCF) Funded | 0 | 0 | 0 | 398 | 398 | 0 | 0 | 0 | 0 | 0
| Academy 2 Land | 1000 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0
| Alperton School Underpinning | 1400 | 1400 | 1400 | 1000 | -400 | 0 | 400 | 400 | 0 | 0
| Wembley Manor Re-build and Expansion | 3000 | 2755 | 2755 | 996 | -1759 | 5000 | 6759 | 1759 | 1500 | 400
| John Kelly | 600 | 324 | 324 | 312 | -12 | 5000 | 5012 | 12 | 0 | 0
| School Loan Scheme | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 750
| Chalkhill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
| BSF Capacity Building | 40 | 40 | 40 | 40 | 0 | 40 | 40 | 0 | 80 | 40
| Family Resource & Children's Centres - Surestart Schemes | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0
| Donnington - Remodelling | 30 | 30 | 30 | 37 | 7 | 0 | 0 | 0 | 0 | 0
| Gladstone Park - Sports Hall | 137 | 137 | 137 | 135 | -2 | 0 | 2 | 2 | 0 | 0
| Kingsbury Green - Extension | 112 | 112 | 112 | 50 | -62 | 0 | 62 | 62 | 0 | 0
| Lyon Park - Phase 1 & 2 Expansion | 30 | 31 | 31 | 0 | -31 | 0 | 31 | 31 | 0 | 0
| Park Lane | 29 | 29 | 29 | 31 | 2 | 0 | 0 | 0 | 0 | 0
| Wykeham - Remodelling | 120 | 120 | 120 | 70 | -50 | 0 | 50 | 50 | 0 | 0
| Wembley High - Extension & Adaptations | 200 | 250 | 250 | 150 | -100 | 0 | 100 | 100 | 0 | 0
| Kilburn Park - Extension Rebuild | 200 | 261 | 261 | 261 | 0 | 0 | 0 | 0 | 0 | 0
School Programme Works
Asset Management Plan:
| Electrical | 11 | 28 | 28 | 26 | -2 | 0 | 2 | 2 | 0 | 0
| Mechanical | 8 | 31 | 31 | 32 | 1 | 0 | 0 | 0 | 0 | 0
| Roofing | 9 | 41 | 41 | 34 | -7 | 0 | 7 | 7 | 0 | 0
| Playgrounds | 0 | 1 | 1 | 0 | -1 | 0 | 1 | 1 | 0 | 0
| Toilets | 3 | 8 | 8 | 3 | -5 | 0 | 5 | 5 | 0 | 0
| Health & Safety | 150 | 152 | 152 | 277 | 125 | 300 | 300 | 0 | 0 | 0
| Windows | 9 | 22 | 22 | 52 | 30 | 0 | 0 | 0 | 270 | 0
| Sixth Form Provision | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0
| Access Initiatives | 372 | 441 | 441 | 385 | -56 | 372 | 428 | 56 | 0 | 0
| Kitchen Equipment | 0 | 59 | 59 | 59 | 0 | 0 | 0 | 0 | 0 | 0
| Additional Asset Management Plan Priorities 1 & 2 - 2005/06 and Future Years | 2119 | 1766 | 1766 | 1322 | -444 | 300 | 579 | 279 | 390 | 3000
| AMP's and Asbestos Survey Fees | 30 | 45 | 45 | 30 | -15 | 40 | 55 | 15 | 40 | 340
Hut Replacement Programme:
| Preston Park | 800 | 794 | 794 | 800 | 6 | 381 | 375 | -6 | 200 | 0
| Uxendon Manor | 0 | 2 | 2 | 0 | -2 | 0 | 2 | 2 | 0 | 0
| Wembley Manor Inf/Jnr | 150 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
| Hut Replacement Works to be undertaken from Prioritised List | 300 | 300 | 300 | 100 | -200 | 0 | 200 | 200 | 0 | 4000
| New Opportunities Fund Works (inc' Chalkhill Sports Hall) | 1143 | 1480 | 1480 | 1418 | -62 | 35 | 97 | 62 | 0 | 0
| Expansion of Secondary School Places (Including Additional Places) | 1100 | 1115 | 1115 | 552 | -563 | 1100 | 1663 | 563 | 1690 | 0
| SEN Schemes | 500 | 516 | 516 | 719 | 203 | 2000 | 1797 | -203 | 5153 | 0
| Asbestos Works | 125 | 128 | 128 | 128 | 0 | 50 | 50 | 0 | 50 | 100
| Contingency for 2005/06 Schemes | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 200 | 1000
| Total School Schemes | 14927 | 15048 | 18468 | 14767 | -3701 | 17018 | 21117 | 4099 | 11003 | 9630
Non- School Schemes
| Transforming Youth Work | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
| Youth Service | 50 | 530 | 530 | 530 | 0 | 0 | 0 | 0 | 0 | 0
| Total Non School Schemes | 50 | 548 | 548 | 548 | 0 | 0 | 0 | 0 | 0 | 0
| Total Schools and Non-Schools Capital Programme | 14977 | 15596 | 19016 | 15315 | -3701 | 17018 | 21117 | 4099 | 11003 | 9630
| Total Children & Families Forecast Capital Programme | 20710 | 23305 | 27820 | 24188 | -3632 | 24018 | 28117 | 4099 | 14463 | 13090

## Environment & Culture
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Environment & Culture Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
| TfL Grant Funded Schemes | 5501 | 5963 | 5963 | 5963 | 0 | 5501 | 5501 | 0 | 5501 | 5501
| Waste Performance and Efficiency Grant | 302 | 302 | 302 | 302 | 0 | 317 | 317 | 0 | 0 | 0
| Estate Access Corridor | 0 | 2105 | 2105 | 2105 | 0 | 0 | 0 | 0 | 0 | 0
| Stadium Access Corridor | 0 | 5108 | 5108 | 5108 | 0 | 0 | 0 | 0 | 0 | 0
2005/06 and Future Years Capital Programme
Environment Individual Schemes
| CCTV at Kensal Rise | 0 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0
| Bridgepark Works | 300 | 405 | 405 | 405 | 0 | 0 | 0 | 0 | 0 | 0
| Organic Waste Collection Service | 0 | 102 | 102 | 102 | 0 | 0 | 0 | 0 | 0 | 0
| Mechanised Street Sweeping Vehicles | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
| Gulley Maintenance Vehicles | 0 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0
| Cycle and Changing Facilities at Offices | 0 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0
| ITP Schemes (Carry forward from 2003/04) | 0 | 125 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0
Environment Programme Works
Highways:
| Pavements and Roads | 3150 | 3150 | 3150 | 3150 | 0 | 2888 | 2888 | 0 | 2900 | 3000
| Streetscene (Transport & Parking BVR) | 70 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0
Parks & Cemeteries:
| Parks Infrastructure | 100 | 144 | 144 | 100 | -44 | 125 | 125 | 0 | 145 | 145
| Cemetery and Mortuary Service | 65 | 65 | 65 | 70 | 5 | 40 | 40 | 0 | 20 | 20
| Delivering the Sports Strategy | 535 | 535 | 873 | 786 | -87 | 285 | 285 | 0 | 535 | 535
| Lighting Outside PFI | 100 | 117 | 117 | 117 | 0 | 0 | 0 | 0 | 0 | 0
| Total Environment Capital Programme | 4320 | 5001 | 5339 | 5213 | -126 | 3338 | 3338 | 0 | 3600 | 3700
Culture Individual Schemes
| Libraries | 0 | 114 | 114 | 117 | 3 | 0 | 0 | 0 | 0 | 0
| Grange Museum Relocation | 0 | 462 | 462 | 870 | 408 | 0 | 0 | 0 | 0 | 0
| Total Culture Capital Programme | 0 | 576 | 576 | 987 | 411 | 0 | 0 | 0 | 0 | 0
| Total Environment & Culture Capital Programme | 10123 | 19055 | 19393 | 19678 | 285 | 9156 | 9156 | 0 | 9101 | 9201

## Housing & CC Adults
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Housing and Community Care: Adults Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
2005/06 and Future Years Capital Programme
Additional Grant Notifications (Ringfenced):
| Improving Information Management Grant | 175 | 175 | 175 | 180 | 5 | 0 | 175 | 175 | 0 | 0
Individual Schemes
| Learning Disabilities Kiosk Project | 0 | 40 | 40 | 120 | 80 | 0 | 0 | 0 | 0 | 0
| Albert Road | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 127 High Road | 0 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0
| 31 Douglas Road | 0 | 40 | 40 | 40 | 0 |  |  | 0
| Brondesbury Road | 295 | 295 | 295 | 0 | -295 | 0 | 0 | 0 | 0 | 0
| Knowles House | 130 | 130 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0
| Total Housing & Community Care: Adults | 600 | 719 | 719 | 509 | -210 | 0 | 175 | 175 | 0 | 0

## Housing & CC Housing
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Housing & Community Care: Housing & Customer Services Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
2005/06 and Future Years Capital Programme
Housing Schemes
| PSRSG and DFG council | 5600 | 6340 | 6340 | 6340 | 0 | 5300 | 5300 | 0 | 5300 | 5300
| New Units | 2969 | 2969 | 2969 | 2969 | 0 | 2969 | 2969 | 0 | 2969 | 2969
| Total Housing Capital Programme | 8569 | 9309 | 9309 | 9309 | 0 | 8269 | 8269 | 0 | 8269 | 8269
Customer Services Schemes
| Brent House One Stop Shops Refurbishment | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Harlesden OSS - Ground Floor Extention to Building | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0
| Total Customer Services Capital Programme | 0 | 54 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0
| Total Housing & Community Care: Housing Capital Programme | 8569 | 9363 | 9363 | 9363 | 0 | 8269 | 8269 | 0 | 8269 | 8269
CAPITAL PROGRAMME 2006/07 TO 2009/10
Housing Revenue Account - Housing Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
2005/06 and Future Years Capital Programme
| ALMO Works and Initiatives | 6500 | 9955 | 9955 | 9955 | 0 | 6500 | 6500 | 0 | 6500 | 6500
| South Kilburn Development | 0 | 0 | 0 | 0 | 0 | 11900 | 11900 | 0 | 0 | 0
| Total Housing Capital Programme | 6500 | 9955 | 9955 | 9955 | 0 | 18400 | 18400 | 0 | 6500 | 6500
| Total Housing Capital Programme | 6500 | 9955 | 9955 | 9955 | 0 | 18400 | 18400 | 0 | 6500 | 6500

## Finance and Corporate Resources
CAPITAL PROGRAMME 2006/07 TO 2009/10
General Fund - Corporate Capital Programme
|  | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2006/07 | 2007/08 | 2007/08 | 2007/08 | 2008/09 | 2009/10
|  | Original | Revised | July 2006 | Updated | Variance | Capital | Updated | Variance | Capital | Capital
| Programme Details | Capital | Capital | Forecast | Forecast | July to | Programme | Forecast | July to | Programme | Programme
|  | Programme | Programme | Programme | Outturn | Forecast | July '06 | Outturn | Forecast
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
2005/06 and Future Years Capital Programme
Individual Schemes
| Customer Relationship Management System | 0 | 238 | 238 | 238 | 0 | 0 | 0 | 0 | 0 | 0
| Quality House Window Replacement | 0 | 125 | 124 | 124 | 0 | 0 | 0 | 0 | 0 | 0
| Security Measures in Town Hall & 3 Muniport Sites | 0 | 85 | 85 | 85 | 0 | 0 | 0 | 0 | 0 | 0
| Cabling to Disaster Site at Gwyneth Rickus Building | 0 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0
| Financial Systems Integration | 225 | 325 | 325 | 325 | 0 | 425 | 425 | 0 | 0 | 0
| Credit Card Hotline Automation - Software package and set up costs | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0
| Town Hall (Grand Hall) Stage Lighting | 0 | 70 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0
| E-mail and Data Storage System (Self Funded) | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
| South Kilburn - Councils Contribution | 1000 | 2000 | 2000 | 0 | -2000 | 1000 | 1000 | 0 | 1000 | 1000
| Brondesbury Road | 0 | 0 | 0 | 295 | 295 | 0 | 0 | 0 | 0 | 0
Programme Works
| Disability Discrimination Act Works | 0 | 87 | 87 | 87 | 0 | 0 | 0 | 0 | 0 | 0
| Minor Works | 100 | 232 | 232 | 232 | 0 | 0 | 0 | 0 | 100 | 100
| Data Network Upgrade | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0
| Electronic Document Management | 0 | 41 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0
| Project Management - to provide additional resources to Service Areas | 400 | 445 | 446 | 446 | 0 | 400 | 400 | 0 | 400 | 400
| Asbestos Surveys | 30 | -30 | -30 | -30 | 0 | 0 | 0 | 0 | 30 | 30
| Inspections of Non-Housing Property | 80 | 160 | 160 | 160 | 0 | 80 | 80 | 0 | 80 | 80
| Priority One Backlog repairs | 1150 | 1324 | 1324 | 1324 | 0 | 1150 | 1150 | 0 | 1350 | 1150
Central Items
| Provision for Liabilities | 300 | 810 | 722 | 514 | -208 | 300 | 300 | 0 | 300 | 300
| Grange Road Acquisition | 0 | 140 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0
| Surestart | 0 | 42 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0
| Elm Road Car Park Lease | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0
| Total Finance & Corporate Resources Capital Programme | 3285 | 6613 | 6525 | 4612 | -1913 | 3355 | 3355 | 0 | 3260 | 3060